## SUN MSP WP 2021
SUN Network Work Plan 2021
[7 empty] | Q 1 (Jan-Mar) |  | Q2 (Apr-Jun) |  | Q3 (Jul-Sep) |  | Q4 (Oct-Dec)
| Sl no. | Activity, Sub-activitiy | Output | Relevant other SUN network/s | Partner organization/s | Organizational contribution | Planned | Status | Planned2 | Status2 | Planned3 | Status3 | Planned4 | Status4 | Comment (if any)
SUN UN Network | 1 | Technical assistance to developing the UNSDCF | UNSDCF framework for nutrition developed |  | BNNC, NNS/IPHN, MOH&FW, MoLE, MOE, MOFood, MOA, MOWCA, DPHE, MOPME, | UNICEF, FAO, WFP, WHO-Technical | Y | Ongoing | Y | Ongoing | Y |  |  |  | All UN network joint work
20th May 2021 | 2 | Technical contribution to developing the Global Action Plan for reducing wasting in Bangladesh | GAP for wasting: Quality improvement of wasting prevention and treatment programme | Donor | BNNC, NNS/IPHN, MOH&FW, MOFood, MOA, MOWCA, DPHE, | UNICEF, WHO, WFP, FAO -Technical | Y | Ongoing | Y | Ongoing | Y |  |  |  | All UN network joint work. UNICEF lead.
Signature of the Network Chair | 3 | Technical support to action track 1 on UN Food System Summit | Dialogues, consultations, online forum and country document on food systems | Business, CSA for SUN, Donor | MoFood, GAIN, CSOs, other nutrition specific and nutrition sensitive ministries | UN network- Technical | Y | Started | Y | Ongoing | Y |  | Y |  | All UN network joint work.
| 4 | Support the Government to prepare for the Nutrition for Growth Summit by preparing independent Summit inputs | Bangladesh's representation in N4G | Donor, Business, SARN | SUN focal point, MOHFW, NNS/IPHN | Technical: UNICEF, WHO, WFP, FAO |  |  |  |  | Y |  | Y |  | All UN network joint work.
| 5 | Technical support to the Ministry of Health and BNNC in planning, implementing and monitoring of NPAN2 | Coordination established, Annual Monitoring report available | CSA for SUN, Business, SARN | BNNC, MoHFW | UNICEF, WHO, WFP, FAO -Technical | Y | Ongoing | Y | Ongoing | Y |  | Y |  | All UN network joint work.
| 6 | Technical support to annual work plan of BNNC | Elaborated annual work plan of BNNC | SARN, CSA for SUN, Business, Donor | BNNC | UNICEF, WHO, WFP, FAO -Technical | Y | Completed | [6 empty] | All UN network joint work.
| 7 | Strengthening Bangladesh National Nutrition Council (BNNC), through policy analysis and multi-sectoral coordination | Improved nutrition programme implementtation across all sectors | Donor | BNNC, National Nutrtion Services (NNS), MoHFW | Technical and financial-WHO SUN UN, |  |  | Y |  | Y |  | Y |  | All UN network joint work.
| 8 | Support Government in strengthening linkages between different service delivery platforms to increase quality and coverage of services. For example health, social protection, agriculture, and education | Increaed coverage and quality of essential nutrition services | CSA for SUN | MOHFW, MOWCA, MOSocial Welfare, MOA, MOPME | Technical: UNICEF, WHO, WFP, FAO | Y |  | Y |  | Y |  | Y |  | All UN network joint work.
| 9 | Support to strengthen nutrition SBCC activities, including using digital platforms, considering the COVID context in nutrition-sensitive sectors with a focus on social protection | Improved positive nutrition practices through Social Behavior Change Communication | CSA for SUN | MoWCA, BNNC, IPHN, | Technical: WFP, FAO |  |  | Y |  | Y |  | Y |  | FAO and WFP. WFP lead.
| 10 | Support to strengthen capacity for better coordination and leadership on contributing to the national nutrition agenda, with particular focus on social safety nets and school feeding | Strengthening governance and leadership to enhance coordination and policy implication across nutrition-sensitive and specific programmes and FNS sectors |  | BNNC & social safety net sectors | Technical: WFP and other UN network | Y | Ongoing | Y | Ongoing | Y |  | Y |  | All UN network joint work. WFP lead.
| 11 | Gather evidence on using cash assistance as a part of social safety net platforms as a way to improve nutritional status of vulnerable populations in selected low-income urban areas | Improved access to nutrition interventions with adequate coverage through specific and sensitive programs in urban areas |  | MoWCA, MoSW | Technical and Financial - WFP, FAO | Y | Ongoing | Y | Ongoing | Y |  | Y |  | WFP lead.
| 12 | Collaborate with nutrition-sensitive social protection programmes and partners to promote a holistic food systems approach to improve nutrition outcomes, with particular focus on urban food systems. | Engaging private sector for improving availabity and access to nutritious diets | Business | MoIndustry, MoFood | TA - WFP, FAO | Y | Ongoing | Y | Ongoing |  |  |  |  | WFP lead.
| 13 | Support the Government of Bangladesh to host independent dialogues and prepare for the UN Food Systems Summit | Strengthening governance and leadership to enhance coordination and policy implication across nutrition-sensitive and specific programmes and FNS sectors |  | MoFood | TA - FAO, WFP, WHO, UNICEF | Y |  | Y |  | Y |  |  |  | All UN network
| 14 | Support MoPME in the rollout of nutrition sensitive home grown school feeding linked to local production of nutritious foods | Rollout of national nutrition senstive home grown school meals |  | MoPME, MoA | Technical and financial assistance WFP, FAO technical | Y | Ongoing | Y | Ongoing | Y |  | Y |  | WFP lead.
| 15 | Technical support to the Government to scale up of rice fortification throught national safety nets as well as for comercial consumption | Improved avaiability, access and consumption of fortified rice |  | MoFood | TA - WFP, FAO | Y | Ongoing | Y | Ongoing |  |  |  |  | WFP lead.
| 16 | Strengthening implementation of essential package of nutrition intervention in health system through Essential Service Packages (ESP) | Improved quality of maternal nutriton | CSA for SUN, Business | National Nutrtion Services (NNS), MoHFW, UNICEF | Technical and financial-WHO, UNICEF Technical-NNS, MoHFW | Y | Ongoing | Y | Ongoing | Y |  |  |  | WHO and UNICEF lead
| 17 | Development of SAM facilitators' module in Bangla and English | Improved quality of wasting treatment programme | CSA for SUN | NNS, MoHFW | Technical and financial-WHO UNICEF | Y | Completed | [6 empty] | WHO and UNICEF lead
| 18 | Facilitate and support breastfeeding and national nutrition weeks | Improved breastfeeding and coordinated nutrition activties across sectors | CSA for SUN | NNS, MoHFW,BBF | Technical and financial-WHO Technical-UNICEF |  |  |  |  | Y |  |  |  | WHO and UNICEF lead
| 19 | Support National Micronutrient Survey through anemia assesment among children 6-59 months and NPNL women | Improved anemia prevention strategies | SARN | NNS, MoHFW, icddr,b | Technical and financial-WHO Technical- SUN UN |  |  |  |  | Y | Not started | Y |  | WHO lead
| 20 | Supporting implementation of breastfeding programme | Improved BF and BFHI programme during COVID | SARN, CSA for SUN | NNS.MoHFW, BSMMU | Technical and financial-WHO, UNICEF | [8 empty] | WHO and UNICEF lead
| 21 | Facilitate dissemination of age and disease specific guidelines | Healthy lifestyle promoted | SARN | NNS.MoHFW, BIRDEM | Technical and financial-WHO, FAO | Y | Ongoing | Y | Ongoing | Y |  | Y |  | WHO lead
| 22 | Upgradation of the Curriculum of BSc in Health Technology (Food safety) course | Food Safety promoted |  | NNS, IPH, MoHFW | Technical and financial-WHO Technical-FAO | Y | Ongoing | Y | Ongoing | Y |  |  |  | WHO lead
| 23 | Analysis of food labelling and composition of packaged food items in context of WHO-SEAR Nutrient profile model | Improved health concern and reduced influence of obesogenic environment |  | NNS, IPH, MoHFW, BSTI | Technical and financial-WHO Technical-NNS, MoHFW, IPH, BSTI, BFSA, FAO | Y | Ongoing | Y | Ongoing | Y |  |  |  | WHO lead
| 24 | Finalization of the National Food and Nutrition Security Policy (NFNSP) Plan of Action (PoA) | NFNSP PoA 2020-2030 | CSA for SUN, SARN, Donor, Business | 19 partner ministries, departments, development partners, CSO, private sector, academia, SBN, Donor, | Technical support by FAO, UNICEF, WHO,WFP | Y | Ongoing | Y | Ongoing | Y |  | Y |  | All UN network. FAO Lead
| 25 | Technical support for research to inform evidence based FNS policies and uptake | Research reports, policy briefs, policy tools, research compendium | SARN | BAU, INFS, BRAC University | Technical- FAO( lead) and other UN network | Y | Started | Y | Ongoing | Y |  | Y |  | UN network engage in technical advisory pannel
| 26 | Launch and dissemination of the e-learning platform for Adolescents and Youth on the Nutrition Challenge Badge | NCB e-learning manual, virtual materials and integrated training course for improved adolescent nutrition | CSA for SUN | FPMU, MoFood, Private sector, | FAO -Technical and WHO, UNICEF | Y | Ongoing | Y | Ongoing | Y |  | Y |  | All UN network. FAO lead.
| 27 | Food safety capacity strengthening of BFSA, MoA, MoFLS in collaboration with academic research and UN partners | Trained food safety officials, food safety monitoring of mobile courts, food safety benchmarks for policies and action plans | Donor, SARN, Business | BFSA, CARS (DU), GTI (BAU), EU | FAO -Technical and WHO | Y | Ongoing | Y | Ongoing | Y |  | Y |  | FAO and WHO, FAO lead.
| 28 | Technical support to mainstreaming nutrition in agriculture, fisheries, livestock, horticulture, urban food systems and resilience related projects. | Nutrition trainings, capacity strengthening, BCC tools and training manuals | Donor | MoFood, DCC, MoFL, CSOs, MoHFW, BFSA, MoA, CHT | FAO -Technical and WFP | Y | Ongoing | Y | Ongoing | Y | Ongoing | Y | Ongoing | FAO and WFP. FAO lead.
| 29 | Mainstreaming nutrition behaviour change for healthy diets in Urban Food Systems | SBCC Strategy for urban nutrition | Business | CSOs, MoLGRD, DCC and MoFood, IFAD | FAO -Technical and WFP, UNICEF |  |  | Y | Started | Y |  | Y |  | FAO lead.
| 30 | Revision of National Dietary Guidelines 2020 | Promotion of healthy lifestyle | CSA for SUN | FPMU, MoFood, MOHFW, BIRDEM, | FAO -Technical and WHO | Y | Ongoing | Y | Ongoing | Y |  | Y |  | FAO and WHO, FAO lead.
| 31 | Technical support on review of nutrition sensitive social safety net programs to BNNC | Position paper on nutrition sensitive safety nets and recommendations |  | UN agencies, Cabinet division | FAO,, WFP -Technical | Y | Started | Y | Ongoing |  |  |  |  | FAO and WFP. FAO lead.
| 32 | Finalization of the National Food Safety Strategy (2022-2026) in alignment with Food Safety Act 2013, NFNSP PoA and NPAN2 | National Food Safety Strategy (2022-2026) | Donor, Business | Private sector, Government, BFSN, CSOs, CAB | WHO, FAO -Technical | Y | Ongoing | Y | Ongoing |  |  |  |  | FAO and WHO. FAO lead
| 33 | Support BNNC in establishing financial tracking mechanism for multi-sectoral investments in nutrition | Financial tracking mechanism established | Donor | MOF, BNNC, NNS/IPHN, MOHFW, MOWCA, MOfood, MOA, MOPME | Technical: UNICEF, WHO, WFP, FAO | Y |  | Y |  | Y |  | Y |  | All UN network. UNICEF Lead
| 34 | Support to strengthen capacity for quality nutrition service delivery and coverage | Coverage and quality of Nutrition services improved | CSA for SUN | NNS/IPHN, MOHFW | Technical: UNICEF, WHO, WFP, FAO | Y |  | Y |  | Y |  | Y |  | All UN network. UNICEF lead
| 35 | Generate evidence on MMS, Community Based Nutrition Program (including SBCC), community-based treatment of acute malnutrition, standarized package of Urban Nutrition services under the framework of PHC for UHC | Research initiated | SARN | MOHFW, MOLGRD, City Corporation, ICDDR,B, BRAC JPG | Techincal and Financial: UNICEF, WHO | Y |  | Y |  | Y |  | Y |  | UNICEF and WHO. UNICEF lead
| 36 | Support capacity building of Govt. to improve nutrition data management, follow-up and data driven decision | Routine analytical report available | Donor | NNS/IPHN, NIPU, MOHFW, WB, NI, FSNIS, NIPN, | Technical: UN network | Y |  | Y |  | Y |  | Y |  | All UN network. NIPU/NNS Lead by UNICEF, FSNIS lead by FAO
| 37 | Strengthen and align routine monitoring systems of DGHS and DGFP, as well as integration of adolescent and urban nutrition data | Interoperability of DGHS and DGFP MIS. Nutrition indicators mainstreamed into DHIS2/3 |  | DG-HS and DG-FP, MIS | Technical UNICEF, WFP, WHO, FAO |  |  |  |  | Y |  | Y |  | All UN network. UNICEF lead.
SUN Donor Network | 1 | Implenetation of research strategy for nutrition which was developed as a priority of 2019-20 SUN JA
| 1.1 | Organize workshop on implementation of research strategy | Workshop held | Donor, UN | BNNC | BNNC, NI (FCDO) | Y | Started | Y
| 1.2 | Provide TA to NNS/IPHN to continue to monitor maternal and child nutrition services delivery to identify gaps and propose corrective actions to accelerate HSSP implementation, particularly in Sylhet and Chattogram divisions. | Increased coverage of registered pregnant women and under-2 children receiving specified nutrition services | Donor | IPHN | Technical Assistance (The World Bank) | Y | Ongoing | Y | Ongoing | Y |  | Y
| 1.3 | Provide TA to NNS/IPHN to complete the refinement of the district action plans and in supporting the district level health managers in tracking the operationalization of the district action plans in 15 districts in Sylhet and Chattogram divisions. | District action plans and identified actions implemented |  | IPHN | Technical Assistance (The World Bank) | Y | Ongoing | Y | Ongoing | Y |  | Y
| 1.4 | Provide Technical Assistance to GoB to Monitor Nutrition Coordination Committees at the District and Upazilla Levels (In Khulna and Barishal) | Meetings held and monitoring structure established | Donor | IPHN, BNNC, FHI360 | Technical Assistance (USAID Bangladesh) | Y | Started | Y | Started | Y | Ongoing | Y | Ongoing
Status | 2 | Nutrition sensitive policy analysis
| 2.1 | Nutrition sensitive policy analysis | Analysis report | Donor, UN | BNNC | BNNC, NI (FCDO) Financial- WHO | Y | Started
Signature of the Network Chair | 2.2 | Validation workshop | Workshop held | UN, CSA for SUN | BNNC | BNNC, NI (FCDO) Financial- NI |  |  |  |  | Y
| 2.3 | Complete and disseminate the assessment to assess the changes in the maternal nutrition and infant and young child nutrition practices among the target beneficiaries due to the project interventions in the project areas under the Nuton Jibon Livelihood Improvement Project (NJLIP) | Report on changes in the maternal nutrition and infant and young child nutrition practices | Donor | ICCDRB | Financial and technical assistance (The World Bank) | Y | Ongoing | Y | Completed
| 2.4 | Continue the feasibility assessment to integrate an evidence-based program of psychosocial stimulation into primary health care services in Bangladesh. | Report on feasibility of implementing psychosocial stimulation into primary healthcare services | Donor | ICCDRB | Financial and technical assistance (The World Bank) | Y | Ongoing | Y | Ongoing | Y |  | Y
| 2.5 | Support the agriculture analytical work on how have diets, their nutritional value, and their environmental cost changed over time in Bangladesh and propose feasible recommendations. | Report on the evolution of diets and related costs in Bangladesh | Donor | World Bank Agriculture Global Practice | Financial and technical assistance (The World Bank) | Y | Ongoing | Y | Ongoing | Y
|  | Provide support to develop an improved mechanisms for BNCC evidence-informed policy making | Knowledge sharing event held, Ministry specific policy brief and case stories developed and shared | Donor | IPHN, BNNC, FHI360 | Technical Assistance (USAID Bangladesh) | Y | Started | Y | Started | Y | Ongoing | Y | Ongoing
|  | Develop Nutrition Evidence Repository for BNNC | Nutrition evidence repository developed and embedded into BNNC website | Donor | IPHN, BNNC, FHI360 | Technical Assistance (USAID Bangladesh) | Y | Started | Y | Started | Y | Ongoing | Y | Ongoing
| 3 | Develop a community-based model to increase coverage of nutrition sensitive interventions
| 3.1 | Develop a model | Approved model | UN, CSA for SUN | BNNC, NNS/IPHN | BNNC, NI (FCDO) | Y | Started | Y
| 3.2 | Pilot the model | Finalized model | Donor, CSA for SUN, UN | BNNC, NNS/IPHN | BNNC, NI (FCDO) |  |  | Y |  | Y
| 4 | Integration of nutrition actions in nutrition-sensitive programs
| 4.1 | Multi-sector nutrition pilot in Moulvibazar District | Ongoing | CSA for SUN | BNNC | BNNC, StC (FCDO, EU) | Y | Started | Y | Ongoing | Y |  | Y
| 4.2 | RCT based research on multi-sectoral nutrition approach | Completed | CSA for SUN | ICDDRB | ICDDRB and StC (FCDO, EU) | Y | Completed
| 4.3 | A national level end line findings dissemination and advocacy workshop organizes on mult-sector nutrition approach | Planned | CSA for SUN | ICDDRB and StC | ICDDRB and StC (FCDO, EU) |  |  | Y
| 4.4 | Deliver nutrition-sensitive and nutrition-specific interventions through livelihoods graduation programme | Ongoing | CSA for SUN | PKSF | PKSF (FCDO, EU) | Y | Started | Y | Ongoing | Y |  | Y
| 4.5 | Sign an MOU with BNNC to strengthen nutrition services in urban areas | Completed | UN | UNDP,BNCC | BNNC, UNDP (FCDO) | Y | Completed
| 4.6 | Delivers urban nutrition interventions in 12 cities and eight towns across eight divisions | Ongoing | UN | UNDP | UNDP (FCDO) | Y | Started | Y | Ongoing | Y |  | Y
| 4.7 | Launching of the ICT based nutrition platform for an unified, systematic, and centralized information flow on nutrition between all relevant ministries and nutrition committees under the BNNC and implement, monitor, and review the progress of DNCC and UNCC's annual nutrition plans at the sub-national level. | Ongoing | Donor | Care Austria with other consortium partners | BNNC, EU Delegation |  |  |  |  | Y
| 4.8 | National Consultation of the Plan of Action for the implementation of the National Food and Nutrition Secuiry Policy (NFNSP) in June (consensus and validation across range of stakeholders) Dissemination of the research findings on | Ongoing | Donor | FAO | FPMU, EU Delegation FAO |  |  | Y
| 4.9 | Dissemination of Research findings | Ongoing | Donor | FAO | FPMU, EU Delegation FAO |  |  | Y
| 4.1 | Support to preparation of SUN Bangladesh Annual Report 21 to SUN HQ | Ongoing | Donor | FAO | FPMU, EU Delegation FAO |  |  | Y
| 5 | Increased availability of evidence to guide multisectoral nutrition programming implementation
| 5.1 | Support to establish a Human Milk Bank (HMB) Network at Dhaka | Four HMB established (ICMH, SSMC, BSMMU and DSH) | Donor | IPHN, BNNC, FHI360, ICMH, BSMMU, DSH, SSMC | Technical Assistance (USAID Bangladesh) | Y | Not Started | Y | Started | Y | Ongoing | Y | Ongoing
| 5.2 | Develop a Policy Brief on Maternal Depression | Policy brief developed and disseminated | Donor | IPHN, BNNC, FHI360 | Technical Assistance (USAID Bangladesh) | Y | Not Started | Y | Started | Y | Ongoing | Y | Ongoing
| 5.3 | Growth Monitoring and Promotion (GMP) and Mobilization for Community based Management of Acute Malnutrition (CMAM) in Khulna City Corporation | Staff trained, GMP sessions conducted and reports are available | Donor | IPHN, BNNC, FHI360, KCC | Technical Assistance (USAID Bangladesh) | Y | Not Started | Y | Started | Y | Ongoing | Y | Ongoing
SUN Business Network |  | Strengthening capacity of Bangladesh Food Safety Authority (BFSA) on Food Safety Management and Nutrition of Micro,Small and Medium Enterprises (MSMEs) with BFSA district inspectors across Bangladesh | Food Safety Officers trained | CSA for SUN | BFSA |  | Y | Ongoing | Y | Ongoing
Date 20/5/2021 |  | Communication Materials to promote healthier diets for adolescents, promoting regenerative agriculture and alternative nutritious products such as sweet potato | Communication materials developed | UN | BNNC, NNS/IPHN |  | Y | Ongoing | Y | Ongoing
|  | Technical Needs Assesment of SBN members for capacity building on nutrition, food safety and business development | Training Need Assesment conducted | SARN | NASCIB |  | Y | Ongoing | Y | Ongoing
|  | Design Nutrition Sensitive Fair Price Shops for RMG factories | Blueprint for nutrition sensitive fair price shop developed | UN | BNNC |  | Y | Ongoing | Y | Completed
Signature of SBN Coordinator |  | Strengthen capacity of sub-national SBN Committee members on nutrition, food safety and business development with clear KPIs for follow up and support | SBN members capacity developed | SARN | NASCIB | BFSA | Y | Ongoing | Y | Ongoing
|  | SBN Strategy Finalization and endorsed by SUN FP | Workshop held | Donor | Ministry of Industries | BNNC, NNS/IPHN | Y | Ongoing | Y | Ongoing
|  | Collaborative Workforce Nutrition Strategy disseiminated | Workshop held |  |  | NASCIB | Y | Ongoing | Y | Completed
|  | COVID-19 recovery grants to SMEs with critical role in improving nutrition outcome of food system | Approved model | UN, CSA for SUN | BNNC, NNS/IPHN | BNNC | Y | Ongoing | Y | Completed
|  | Formation of National SBN Committee | Finalized model | Donor, CSA for SUN, UN | BNNC, NNS/IPHN | NASCIB | Y | Ongoing | Y | Completed
|  | Organize Food Frontier Urban Innovation Challenge 2021 to identify innovative startups and youth entreprenuers | 3 Innovative Business Model initiated |  |  | Ministry of Industries | Y | Ongoing | Y | Completed
|  | Build Capacity of cohort of graduate students on Food Safety and Nutrition | 100 graduate students are trained in food safety and nutrition | Donor, UN, CSA for SUN, Business | INFS and BAU |  | Y | Not Started | Y | Not started
|  | Investor Nights to connect innovative companies to investors | SBN members connected to impact investors | Donor | Bangladesh Angels Network | BNNC, NNS/IPHN | Y | Ongoing | Y | Completed
|  | Establishment of National SBN Committee leady by private sector | National Committee Established | UN | Ministry of Industries | BNNC, NNS/IPHN |  | Not Started |  | Not started
|  | Assess and cluster SME needs (e.g. by size, value chain) for finance, technical assistance and business development support. | SMEs assesed | CSA for SUN | NASCIB |  | Y | Completed |  | Completed
|  | Policy Advocacy meetings with private sector as part of UNFSS | Workshops/meetings held | Donor, UN, CSA for SUN, Business | FAO | INFS and BAU |  |  | Y | Completed
|  | Strengthen the capacity of SME support providers to enhance the relevance and impact of their service offerings to support SMEs | Service Providers trained | CSA for SUN | WFP | Bangladesh Angels Network |  |  |  | Not started
|  | Policy advocacy meetings with SUN Network and Private Sector | Research or kenowledge management relevant activities supported | UN, Donor, CSA for SUN, Business | BNNC | Ministry of Industries |  |  |  | Not started
SUN Academia & Research Network (SARN) | 1 | Implenetation of research strategy for nutrition which was developed as a priority of 2019-20 SUN JA
Date- 18/05/2021 | 1.1 | Organize workshop on implementation of research strategy | Workshop held | Donor, UN | BNNC | Technical- BNNC, NI Financial-NI | Y |  | Y | [5 empty] | Discusiion has initiated
| 1.2 | Conduct assessment of childhood nutrition status | Survey report | Donor, UN, CSA for SUN | INFS, icddrb, NNS, BNNC, JPGSPH | Technicial- INFS, icddrb, NNS, BNNC, JPGSPH, UN network Financial- UN/Donor network member |  |  | Y |  | Y |  | Y |  | Subject to availability of fund. After complition of the survey, a validation workshop will be organized and a policy brief will be dveloped.
| 2 | Nutrition specific, sensitive, social safety net policy, program review/analysis
Name & Signature of the SARN Network Chair (Acting) | 2.1 | Conduct nutrition review/analysis | Analysis report | Donor, UN | BNNC,Cabinet division, NNS/IPHN, NIPIN | Technical- BNNC, NI, WHO, FAO, UNICEF, NIPIN, FHI 360 Financial- WHO, NI, WFP |  |  | Y |  | Y |  | Y
Prof. Nazma Shaheen | 2.2 | Organize validation workshop | Workshop held | UN, CSA for SUN | BNNC,Cabinet division, NNS/IPHN, NIPIN | Technical- BNNC, NI, WHO, FAO, UNICEF, NIPIN, FHI 360 Financial- WHO, NI, WFP |  |  |  |  | Y
| 2.3 | Develop policy briefs | Policy brief developed | Donor, UN, CSA for SUN, Business | BNNC, Cabinet division, NNS/IPHN, NIPIN | Technical- BNNC, NI, WHO, FAO, UNICEF, NIPIN, FHI 360 Financial- WHO, NI, WFP | [6 empty] | Y
| 3 | Develop a community-based model to increase coverage of nutrition sensitive interventions
| 3.1 | Develop a community based model | Approved model | UN, CSA for SUN | BNNC, NNS/IPHN | Technical- BNNC, NI | Y |  | Y
| 3.2 | Piloting of the model | Finalized model | Donor, CSA for SUN, UN | BNNC, NNS/IPHN | Technical- BNNC, NI | [6 empty] | Y
| 4 | Support to SUN Focal point for preparation of N4G Summit
| 4.1 | Support to generate evidences, develop background paper/policy brief as needed | Report on evidences/ background paper/ policy brief etc. | Donor, UN, CSA for SUN, Business | BNNC | Technical- BNNC |  |  | Y |  | Y |  | Y
| 4.2 | Support to organize workshops/meetings | Workshops/meetings held | Donor, UN, CSA for SUN, Business |  |  |  |  | Y |  | Y |  | Y
| 5 | Support other SUN networks in research or kenowledge management relevant activities as needed
| 5.1 | Support in research or kenowledge management relevant activities | Research or kenowledge management relevant activities supported | UN, Donor, CSA for SUN, Business | BNNC | Technical- BNNC |  |  | Y |  | Y |  | Y